## Sheet1
Prescription Upload
Point's | Description | Time Line
Diagnostic Prescription -> In The Pathology Section Medicine Prescription -> In The Pharmacy Section | 1) Prompt Writing That can handle image processing for. (Diagnostic,Medicine) 2) Creating table that can store extracting text into them with price and dosage. (mapped with prescription table) | 4.0 hr 5.0 hr
User Approval & Booking
Point's | Description | Time Line
User Receives: App notification and WhatsApp notification. | 1) Logic for app notification 2) Logic for Whatsapp notification (wabaId and other cred for whatsapp msg) | 3.5 hr 5.0 hr
User reviews the admin-approved details. | 1) Creating end point for (approving) 2) Logic for approve then reflect into the admin pannel | 0.5 hr 8.0 hr
User approves and Books the test slot. (for diagnostics)
Confirms the medicine order. (for pharmacy)
Tentative Pricing & User Confirmation (Before Admin Review)
Point's | Description | Time Line
Diagnostics Tentative test prices are fetched from the Lab Master. Quote display logic:Total 4 lab quotes shown Lowest 2 priced labs Other 2 labs from user-selected preferred labs (if selected) If no labs are selected by the user, only the lowest 2 labs are shown A disclaimer is displayed stating that prices are subject to change. User confirms the tests and selected lab(s). Medicines Tentative medicine prices are fetched using references from 1mg / PharmEasy. Disclaimer displayed stating that prices are indicative and subject to change. User confirms the medicines. Once the user confirms, the request moves to the Admin Web Panel for review. |  | 8.0 hr
Admin Review & Finalization
Point's | Description | Time Line
Edit medicine or test names. Add or remove items. Correct dosage (for medicines) Update pricing if required. Once admin finalizes: The updated details are sent back to the user for final approval. | 1) Show the prescription (text, price, dosage) in the web table formate with full CRUD. (admin can do) 2) Preparing Logic for Image To Text Extracting and store into the datadase. 3) Creating end point and get back to the user for user approval. | 2 day
Customized push Notification Implementation
Point's | Description | Time Line
A section in the web panel to add the push notification and an optional image with it. On click of "Send," it should go to all the Android and iOS users instantly. Save the notification in a table and show it in the descending order. In the app, the notification should show up in the notification section. Create an API to fetch top X notifications and to be used in the notification center screen. |  | 2 day
Implement new subscription plans
Point's | Description | Time Line
Creating New Subsription Plans (from the database) |  | 4.0 hr
Send welcome letter to customers mail id
Point's | Description | Time Line
Send an email to the customer after his subscription is approved/activated by admin (customer's subscription should start from that day) The email will have text icluding - customers name, their plan start/end date and also a pdf letter attachment according to their subscription plans | 1) Creating new email templates 2) PDF Sent logic | 8 hr